NorDig Accessibility Group

Minutes from group meeting

Time:	  	Tuesday  10th.  February 2025

Location: 	Teams online meeting

Participants:	Peter Mølsted, Chairman

Per Tullstedt, Terracom 
Jan Müller, Dolby

- Minutes from last meeting

Minutes from NorDig Accessibility meeting 22th. January 2025 approved.

- Input for this meeting

Peter: Summary on feedback of NorDig questionnaire about TV accessibility 22_01_2025

- Accessibility package

“NorDig accessibility package ver. 1.0” was released 7th. November 2024.

Peter have sent information about “NorDig accessibility package” to the disability organisations in the Nordics countries and Ireland for information.
Only feedback from Ireland and that was very positive.

- Study background, requirements and needs for Accessibility
Updated summery of NorDig questionnaire about TV “Summary on feedback of NorDig questionnaire about TV accessibility 22_01_2025”

The summery document was discussed and approved, it will be sent to NorDigT and a 2 slides presentation to Excom to be done.
AP/ Peter to make a 2 slides status presentation to Excom about the results from the work in NorDig Accessibility group – Peter to send the presentation to Per.

- IAAP Nordic

NorDig have been invited to participate in IAAP Nordic, Accessibility workshop and event 3-4 February in Helsinki and online.

Jan had participated in IAAP Nordic and reported that it was not a technical event, focus was mainly on content, use of AI for content production and regulations. There was nothing about development of HbbTV based accessibility services. All Nordic Public services broadcasters was represented at the even except for YLE.

- Actions list

Proposals and actions for NorDig Accessibility group.

Updated 10.02.2025.

| No. | Title | Description | Owner | Status |
| --- | --- | --- | --- | --- |
| 1 | EU regulations | Examine current and future requirements regarding accessibility (see also presentation from Sony about EU regulations) 19.12.23: New accessibility requirements from Traficom, Finnish Transport and Communications Agency. The Traficom requirements are monitoring the new EU accessibility regulations and are very widely on user interface for tv and internet. Kari will be in a meeting with Traficom 10th. January about more details in the requirements and implementations. https://www.traficom.fi/en/traficom/accessibility/new-accessibility-requirements 16.02.24: Ofcom requirements was discussed. 29.05.24: Digital Europe drafting document with recommendation to meet EU requirement. ETSI special taskforce working on technical rapport about The European Accessibility Act (EAA), the rapport shall be ready in September. There are no requirements in the European Accessibility Act (EAA) that NorDig spec. does not include, no need for changes in this context. For more information see links in item 11. Links to relevant information. 14.08.24: EBU – MAT group are working on recommendation document about AD production. New EU regulation discussed – no impact on our ongoing work with accessibility in NorDig. AP/ Mark to check new requirements from Ofcom and the EBU AD production requirements. 10.09.24: No comments 30.09.24 EBU AD production requirements document expected to be released ultimo October 2024. New requirements from Ofcom expected to be announced ultimo October 2024. 23.10.24 Since Richard is no longer in the group, a new one must be found who can help us with information about accessibility work in Ofcom and DTG. - No news / updates about EBU AD production requirements document. - No news about new accessibility requirements from Ofcom. 06.11.24: Mark will rapport from DTG accessibility group. 26.11.24: Mark informed that Richard Moreton (former Samsung) have joined DTG and shall work with updating the U-Book. Paul informed that Traficom (Finnish Transport and Communications Agency) have published new document (in Finnish) with updated accessibility requirements with reference to “ETSI TR 104 060 v0.0.9 (2024-09). 09.12.24: Mark informed that Richard Moreton (former Samsung) a working as consult for DTG and with updating the U-Book. 09.01.25: The European Accessibility Act (EAA), the directive comes into force on 28 June 2025, in this regard, there are many activities underway, especially in Sweden, around being able to meet the new requirements. 22.01.25: No comments. 10.02.25: No comments. | All | In progress |
| 2 | Public services broadcasters | 29.05.24: Closed. | Peter | Closed |
| 3 | NorDig IRD manufacturers | 14.08.24: Closed. | Peter | Closed |
| 4 | Interest organisations | Contact relevant interest organisations for people with various physical disabilities about their needs and wishes for the NorDig specifications. AP/ Mark, to contact disabilities organizations in UK and other relevant organisations. AP/ Peter to contact disabilities organisations in the Nordic countries. --------------------------------------------------------------- Text removed - can be found in minutes from previous meeting. --------------------------------------------------------------- 12.06.24: We got feedback on our questionnaires from Denmark, Sweden, Finland and Irland, but still not from all special interest organizations. AP/ Peter to follow on the organisations and make a summery with feedback on the questions. 14.08.24: AP/ Peter to make a summary on the feedback on the questionnaires. 28.08.24: To be done 30.09.24: To be done. 26.11.24: We got now in all 10 answered questionnaires. AP/ Peter to make a summary on the feedback on the questionnaires – in process. 09.12.24: It was agreed to make a summery with extracting from the feedback on the questionnaire, needs and ideas for accessibility services including proposal for actions. AP/ Peter to make a new version of a summery. 09.01.25: - It was agreed to make a new schematic summery including answers from all group in bullet form. AP/ Peter to make a new summery on the feedback on the questionnaires. 22.01.25: AP/ Peter to update the summery with input from the meeting. 10.02.25 Done, item closed | Mark / Peter | In progress |
| 5 | Existing solution and guidelines | 10.09.24: Closed. | All | Closed |
| 6 | NorDig supported services | Development of NorDig specification / document with an overview of accessibility services, implementation options and guidelines supported by NorDig. --------------------------------------------------------------- Text removed - can be found in previous meeting minutes. --------------------------------------------------------------- 26.11.24: “NorDig accessibility package ver. 1.0” was released 7th. November at NorDig website and press release have been sent out. We have not received any comments on the release. 09.12.24: Closed | Peter/ Per | Closed |
| 7 | HbbTV services | Description of accessibility services supported by HbbTV. --------------------------------------------------------------- Text removed - can be found in previous meeting minutes. --------------------------------------------------------------- 12.06.24: AP/ Juha and Peter to update “Accessibility services based on HbbTV_NorDig recomandations _draft 001” with inputs prom the meeting. AP/Juha, initiatives and plans for HbbTV accessibility services in Finland when possible. AP/Juha information about project with accessibility services based on HbbTV in Spain. 10.09.24: Poul informed that today in Finland it is mostly the PayTV broadcasters who have HbbTV services on air, with links to their OD applications. 30.09.24: Juha informed that there is now news about initiatives and plans for HbbTV accessibility services in Finland. The project with accessibility services based on HbbTV in Spain had a fine presentation at IBC. 23.10.24 Possibilities to promote / inform about the possibilities with HbbTV in connection with NorDig releasing the accessibility package were discussed. AP/ Peter to contacts the accessibility responsible of the public service broadcasters to hear if there is interest in possibly organising a seminar on the subject. 06.11.24: AP/ Peter to contacts the public service broadcasters when the “NorDig Accessibility package” is released. 26.11.24: The press release including information about HbbTV based accessibilty services have also been sent to persons responsible for accessibility at the Nordic public service broadcasters including questions about if there is interest in a possible seminar / workshop about HbbTV based accessibility services. 09.12.24: We only got feedback from NRK and they don’t have plans for HbbTV, therefore no interest for a workshop. 09.01.25: AP/Peter to contact the broadcasters asking where their focus is and where can we help in terms of accessibility service. 22.01.25: AP/Peter to contact the broadcasters asking where their focus is and where can we help in terms of accessibility service and include presentation about HbbTV based accessibility services for info. 22.01.25: No feedback | Juha | In progress |
| 8 | Universal remote control | 28.08.24: Closed. | All | Closed |
| 9 | Accessibility menu | 14.08.24: Closed. | All | Closed |
| 10 | Best practice | 28.08.24: Closed. | All | Closed |
| 11 | Collaboration with other organisations | 06.11.24: Closed – see activities moved to item 1. | Mark/ Peter | Closed |
| 12 | HbbTV Accessibility services in Germany | 12.03.24: Klaus Merkel, ARD/ RBB (formerly IRT) attended the meeting to talk about Accessibility services based on HbbTV. ARD has many years of experience with the development and implementation of accessibility services in HbbTV and has many services “on air” both for live TV and on demand. HbbTV apps as general interface to accessibility services is something we need to investigate more for NorDig. --------------------------------------------------------------- Text removed - can be found in previous meeting minutes. --------------------------------------------------------------- 30.09.24: Klaus Merkel will participate at next NorDig Excom meeting with presentation about Accessibility services based on HbbTV and a dialogue about development of Accessibility services in NorDig countries and possible collaboration. 23.10.24 Klaus participated at the NorDig Excom meeting 17th. October with a presentation about accessibility services based on HbbTV, experience in German, developments and benefits. The Excom members was positive and interested in the subject. 06.11.24: No comments 26.11.24: To follow up later. 09.12.24: No comments. 22.01.25: Standby - to follow up later. | Peter | In progress |

- Related documents latest version (see nordig.org)

- Sony_EUaccessibilityact_NordigExcom19Oct2023 (EU regulation about Accessibility)

- 2023.10.19NRKAccessServices-NorDig (NRK Accessibility Services)

- Feedback from NorDig broadcasters_ Accessibility services_draft001

- NorDig IRD v3.2 supported Accessibility Services_draft 003

- NorDig Universal Accessibility remote control_draft001

- Siri Antonsen, NRK “To Nordig from NRK-some technical needs for Accessibility in the future”

- Questions regarding TV accessibility for the organisations_draft003_RM

- Accessibility services based on HbbTV.pdf (Klaus Merkel, ARD)

- HbbTV presentation Klaus Merkel_Summery_v1 (Peter Mølsted)

- NorDig Public Services broadcaster_Accessibility now and future_summery 2024_draft002

- NorDig IRD spec_Accessibility ver. 3.2.2_draft002

- NorDig Accessibility package 2024_draft001
NorDig IRD and RoO v3.2.1 supported Accessibility Services_draft 006

- Accessibility services based on HbbTV_NorDig recomandations _draft 005

- Amendment document to NorDig Unified Requirements v3.2.1 concerning Accessibility_draft005

- NorDig Rules of Operation ver. 3.2.2_audio_renumbering_draft004

- “NorDig accessibility package ver. 1.0” -- released 7th. November 2024

- Summery_answers on NorDig questionnaire regarding TV accessibility _UK version draft001

- Extract_Summery of NorDig questionnaire about TV accessibility  draft002   07_01_2025

- Summary on feedback of NorDig questionnaire about TV accessibility 22_01_2025

- Links to relevant information and documents (updated 10.02.25)
HbbTV organisation /V Accessibility:

https://www.hbbtv.org/wp-content/uploads/2021/09/Nigel-Moore-HbbTV-Webinar-Accessibility-2021-09-21.pdf

DTG U-Book, Accessibility:

https://dtg.org.uk/resource/u-book-4/

DTG guide to clear speech:

https://dtg.org.uk/resource/a-guide-to-clear-speech/

GARI Global Accessibility Reporting Initiative:

https://www.gari.info/
Draft ETSI EN 300 468 V1.17.1 (2022-07) (specification for SI):
https://www.etsi.org/deliver/etsi_en/300400_300499/300468/01.17.01_20/en_300468v011701a.pdf

ETSI TR 104 060 Guidance on how to apply the EN 301549 to digital television receivers.

ETSI intro page for ETSI EN 301 549: https://www.etsi.org/human-factors-accessibility/en-301-549-v3-the-harmonized-european-standard-for-ict-accessibility?jjj=1716971215908

EN 301 549 V3 the harmonized European Standard for ICT Accessibility

EN 301 549 V3 the harmonized European Standard for ICT Accessibility
It includes links to two other European Directives (European Directives 2016/2102 and 2019/882)

- European Directives 2015/0278 :  on the approximation of the laws, regulations and administrative provisions of the Member States as regards the accessibility requirements for products and services (Text with EEA relevance).

- European Directives 2016/2102: on the accessibility of the websites and mobile applications of public sector bodies (Text with EEA relevance).

- European Directives 2019/882: on the accessibility requirements for products and services (Text with EEA relevance).

https://www.etsi.org/deliver/etsi_en/301500_301599/301549/03.02.01_60/en_301549v030201p.pdf
https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:52015PC0615&from=EN

EU EAA "home page" European accessibility act - Employment, Social Affairs & Inclusion - European Commission (europa.eu)

Project with accessibility services based on HbbTV in Spain: https://www.anglatecnic.com/project/fingertext

Information about that the pay tv operator will stop distribution in Swedish DTT network from the end of 2024:

https://www.boxer.se/nyheter/boxer-andrar-distribution-av-tv-tjanster

Clear voice / Dialogue Enhancement:
Bayerischer Rundfunk test of "Dialogue+":
https://www.br.de/presse/inhalt/pressemitteilungen/br-dialog-plus-pilotphase-100.html

WDR: https://www.audioblog.iis.fraunhofer.com/wdr-fraunhoferiis-next-generation-audio

ARD/RBB: https://www.hbbtv.org/wp-content/uploads/2021/09/210921_Accessibility_services_based_on_HbbTV_Klaus_Merkel.pdf
SVT: https://b2b.svt.se/  https://b2b.svt.se/program/komplett-leverans/technical-specifications.html

IAAP Nordic, Accessibility workshop and event 3-4 February 2025 in Helsinki and online

https://iaap-nordic.org/en/whats-up/

- Meetings
Telco / Teams meeting, Tuesday 4th March from 14.00 to 15.00 CET.

Note: meeting minutes and other relevant documents will be uploaded at the NorDig website (nordig.org) at member’s area in Accessibility Group / documents.
https://nordig.org/groups/accessibility-group/